## June 2011 (hidden)
UNIFIED NM PLATFORM : STATUS REPORT
S.No | Task | Timeline |  | Comments
|  | Start Date | End Date
1 | AP profile workflow finalized. Database for AP device type fixed | 2011-05-31 | 2011-06-02 | Selective Update for AP type devices. Development continuation of AP type devices, over a DB
2 | ODU [16 Mbps] Monitoring Propritery Plugins, Creation and Integration | 2011-05-31 | 2011-06-07 | Propritery Plugins would be further used for the Monitoring of ODU type 16Mbps and 100 Mbps
3 | Work Flow Details Database schema fixation | 2011-06-08 | 2011-06-11 | Core of NMS has to be shifted to MySql database. Workflow for the same has been fixed, database schema would be developed and fixed till 11-Jun.
4 | AP Integration Completion. System Ready for Final release for AP Type Device | 2011-06-08 | 2011-06-13 | The AP type of devices would be completed Testing would be started, and be deployed for the client
5 | ODU and IDU Monitoring feature development and Dashboard Creation for the both | 2011-06-13 | 2011-06-18 | Dashboard and the device information on the same page would be displayed to the user. Next step would be to integrate configuration parameters in the UI.
6 | ODU Management : Master / Slave | 2011-06-13 | 2011-06-18 | Database Fixation would be completed till 13-Jun, Monitoring of both the devices would be shifted to a single person. One person would be shifted over configuration management of the Device
7 | Trap Manager for NMS | 2011-06-13 | -- | One person would be assigned over VNL unicast device discovery and trap manager and translator. Database creation for Inventory Management and Error/Alerts Management

## July 2011 - Plan
UNIFIED NM PLATFORM : STATUS REPORT
S.No | Task | Timeline |  | Comments | Resource
|  | Start Date | End Date
1 | Inventory Management | 2011-07-06 | 2011-07-18 | Control panel to remove / add / edit / disable / enable, the devices or a group of devices in the network. | YK
2 | VNL Unicast Discovery | 2011-07-01 | 2011-08-05 | VNL's proprietary TCP based discovery of supporting network elements, ODU, IDU. | RG
3 | ODU Configuration Management | 2011-07-06 | 2011-07-18 | Panel for Multiple ODUs Configuration | AS
4 | ODU Monitoring and Dashboards | 2011-07-18 | 2011-08-05 | Performance Log monitroing + Services Dashboards [ CRC / PHY Errors / RSSI / Freq channel / BW / Tx-Rx packet / Radio Frame Level / Modulation ] | YK
5 | ODU Firmware Management | 2011-07-18 | 2011-08-05 | Central page to manage the firmware of multiple ODUs, starting from Slave and moving up to Master. [ Site Management] | AS
6 | Testing |  |  | ongoing ¦ Testing framework Development | CSK
7 | Alert Management | 2011-07-06 | 2011-07-20 | Alarm Masking, Alarm events and actions [ As per Vodafone NMS requirements ] | RK
8 | Network Map Enhancement | 2011-07-06 | 2011-07-13 | Better Network maps to display network elements and their status | PS
9 | Intelligent ODU Configuration + Scheduling + Bandwidth Management + Feedback Feature Integration | 2011-07-18 | TBD ( 5 Aug ) | Expected date of release with ODU configuration, plus inventory is 18-Jul; after that feedback would be awaited and new features or enhancement would be started | RK
10 | Audit Log | 2011-07-20 | 2011-08-05 | User action trail. User to device or NMS interaction trail | PS
11 | Bug Resolution, Phase 1 | 2011-07-13 | 2011-07-20 |  | PS
12 | Bug Resolution, Phase 2 | 2011-08-05 | 2011-08-15 |  | PS / RK

## July 2011 (hidden)
UNIFIED NM PLATFORM : STATUS REPORT
S.No | Task | Timeline |  | Comments | Resource
|  | Start Date | End Date
1 | Inventory Management | 2011-07-06 | 2011-07-18 | Control panel to remove / add / edit / disable / enable, the devices or a group of devices in the network. | YK
2 | VNL Unicast Discovery | 2011-07-01 | 2011-07-30 | VNL's proprietary TCP based discovery of supporting network elements, ODU, IDU. | RG
3 | ODU Configuration Management | 2011-07-06 | 2011-07-18 | Panel for Multiple ODUs Configuration | AS
4 | ODU Monitoring and Dashboards | 2011-07-18 | 2011-07-30 | Performance Log monitroing + Services Dashboards [ CRC / PHY Errors / RSSI / Freq channel / BW / Tx-Rx packet / Radio Frame Level / Modulation ] | YK
5 | ODU Firmware Management | 2011-07-18 | 2011-07-30 | Central page to manage the firmware of multiple ODUs, starting from Slave and moving up to Master. [ Site Management] | AS
6 | Testing |  |  | ongoing ¦ Testing framework Development | CSK
7 | Alert Management | 2011-07-06 | 2011-07-20 | Alarm Masking, Alarm events and actions [ As per Vodafone NMS requirements ] | RK
8 | Network Map Enhancement | 2011-07-06 | 2011-07-13 | Better Network maps to display network elements and their status | PS
9 | Intelligent ODU Configuration + Scheduling + Bandwidth Management + Feedback Feature Integration | 2011-07-18 | TBD ( 5 Aug ) | Expected date of release with ODU configuration, plus inventory is 18-Jul; after that feedback would be awaited and new features or enhancement would be started | RK
10 | Audit Log | 2011-07-20 | 2011-07-30 | User action trail. User to device or NMS interaction trail | PS
11 | Bug Resolution, Phase 1 | 2011-07-13 | 2011-07-20 |  | PS
12 | Bug Resolution, Phase 2 | 2011-07-30 | 2011-08-10 |  | PS / RK

## July 6 - July 14
UNIFIED NM PLATFORM : STATUS REPORT
S.No | Task | Timeline |  | Comments | Status
|  | Start Date | End Date
1 | Inventory Management | 2011-07-06 | 2011-07-11 | Database Fixed | Implementation Pending
2 | VNL Unicast Discovery | 2011-07-01 | 2011-07-14 | Protocol Created, communication has started with device, next task making it Multi Threaded | In Process
3 | ODU Configuration Management | 2011-07-06 | 2011-07-14 | Database Fixed ¦ Integration started | In Process
4 | Alert Management | 2011-07-06 | 2011-07-14 | Database Fixed ¦ Clear Alarms Integration ¦ Current Alarm Integration | In Process
5 | Network Map Enhancement | 2011-07-06 | 2011-07-14 | Algorithm Modified ¦ Javascript Based Topology Map integration | Code Freezed
6 | Audit Log | 2011-07-06 | 2011-07-11 | Database Fixed ¦ Workflow fixed ¦ Integration in application | Implementation Pending
7 | AP | 2011-07-08 | 2011-07-14 | Selective Updates Bug fixing | In Process