## Features
# | Module |  | Feature | Description | Priority | Phase | Currently Present
1 | Administration | [6 empty] | A
|  | a | Audit Log | Configuration part: trace and trail | High | 2 | No
|  | b | User / Role Management | Enhancement : HTTP auth To Session Maintain |  | 1 | Yes
|  | c | Device Assignment | Device to User Mapping |  | 1 | Yes
|  | d | System Settings | NMS configuration and settings : | Low | 1 | Partial
|  | e | Upgrade System | NMS version upgrade |  | 1 | Partial
|  | f | DB Backup / Restore | DB to be implemented : MySQL |  | 2 | No
2 | Monitor | [6 empty] | F
|  | a | Data Traffic [SNMP] | MRTG graphs Done ¦ More custom graphs to be implemented : TBD Ask for Required graphs : Device supported |  | 1 | Partial
|  | b | Alarms with categorization | Alarm Defination : thresholds : TBD Intelligent Alarms |  | 1 | Partial
|  | c | Device Information / Services | Send : fetch mode |  | 1 | Yes
|  | d | User Dashboard | User monitored params |  | 1 | Partial
|  | e | Device Dashboard | Device based |  | 1 | Partial
|  | f | Generic Device Monitoring | Third party device monitoring if existing into the network |  | 1 | Yes
|  | g | Graphical / Geographical View | Nagvis : Need improvement |  | 1 | Yes
|  | h | Acknowledgement of Alarms / Notifications/Resolution | Docket management system ¦ Email |  | 2 | No
|  | i | Connected Users | For AP only.. CGI unknown for other devices : TBD |  | 2 | No
3 | Configuration : Device Level | [6 empty] | C
|  | a | Auto Discovery [Multiple Instances] | Need discussion : IP [SNMP based] UPnP |  | 1 | Partial
|  | b | Profile Templates | Done for AP, for rest .. Remaining : TBD
|  | c | Config Task [To be defined in details, per case basis + Scheduling] | On Off TBD |  | 2 | No
|  | d | Factory Reset | At the device end : for AP.. For other devices : Info needed |  | 1 | Yes
|  | e | Firmware Upgrade [Manual / Scheduled] | Maual done ¦ Scheduled Remaining |  | 1 | Yes
|  | f | Firmware files Management |  |  | 2 | No
|  | g | Individual Device Management [HTTP Frame] | Done for AP ¦ tested for P2P |  | 1 | Yes
|  | h | Route Management |  | Low | 3 | No
|  | i | Schedule Management | Other regular action scheduling : TBD |  | 2 | No
auto provisioning
4 | Reporting | [6 empty] | P
|  | a | Save Report on Server | Saving the filters |  | 2 | No
|  | b | Historical Reports |  |  | 1 | Partial
|  | c | Graph based Analytics | Need Discussion |  | 2 | No
5 | Accounting & Authentication | [6 empty] | S
|  | a | Usage, Time based billing | Hotspot Billing | Low | 2 | No
|  | b | ID based on IP/Mac/Username | through Radius | Low | 2 | No
|  | a | RADIUS Integration [with Proxy] | Through Radius | Low | 2 | No
6 | Interfaces
|  | a | Webbased Portal | On |  | 1 | Yes
|  | b | SNMP Northbound | important [ SNMP / XMLSOAP ] : Specification needed |  | 2 | No
|  | c | Notification System [SMS/EMAIL] | Nagios Part |  | 1 | Partial
7 | Scalability / Redundancy
|  | a | Handling Large Networks & Operation | need to be discussed |  | 3
|  | b | Distributed System | thin client Architecture |  | 3
|  | c | Device Failover Management | Requirement Specify? |  | 3
8 | Planning
|  | a | Wireless Coverage Planner [Indoor / Outdoor] |  |  | 3
|  | b | Network Design |  | Low | 3
|  | c | Signal Strength |  | Low | 3
9 | device list : integration
|  | a | APs |  |  | 1 | Yes
|  | b | Switches – 24 / 8 Port |  |  | 2 | No
|  | c | IP Radios |  |  | 2 | No
|  | d | E1 Radios |  |  | 2 | No
|  | e | IP Cameras | Only the config and alarm log part need to be captured | Low | 2 | No
|  | f | Home Gateway / Enterprise Gateway / Switch 4 Port | Not on high priority | Low | 3 | No

## Features 1 July
# | Module |  | Feature | Description | Priority | Phase | Currently Present
1 | Administration | [6 empty] | A
|  | a | Audit Log | Configuration part: trace and trail | High | 2 | No
|  | b | User/ User Group / Role Management | Enhance - Extend role of a single user too | High | 1 | Partial
|  | d | System Settings | NMS configuration and settings : | High | 2 | Partial
|  | e | Upgrade System | Enhance - Automated NMS version upgrade | High | 2 | Partial
|  | f | DB Backup / Restore | Backup of Data dump | High | 2 | No
|  | g | Support for secure encrypted VPN Tunnels / VLAN integration | To monitor and manage remotly located devices | Med | 2 | No
|  | h | User Communication Controlling | Ability to control the user-user communication connected to the same AP or different APs of the same controller. | Med | 3 | No
|  | i | Device Communication Controlling | Ability to control AP-AP communication connected to the same or different controllers. | Med | 3 | No
|  | j | Support for management of third-party devices. Vendor to specify the requirements and limitations. |  | Med | 3 | No
2 | Monitor | [6 empty] | F
|  | a | Data Traffic [SNMP] | MRTG graphs Done ¦ More custom graphs to be implemented : TBD Ask for Required graphs : Device supported | High | 2 | Partial
|  | b | Alarms | Alarm Masking / Removal of duplicate alarms / Alarm categorization / Alarm Acknoweledgement / Alarm Action / Alarm to User or User Group Mapping [Contact Group] | High | 2 | No
|  | c | Device Information / Services | Send : fetch mode | High | 2 | Partial
|  | d | User Dashboard | User's Selected Devices and Services Monitoring | High | 2 | No
|  | e | Device Dashboard | Device Specific Dashboard / Device type Specific Dashboard / Device Group Dashboard [Common Dashboard NMS] | High | 2 | Partial
|  | f | Generic Device Monitoring | Generic IP based device present in network should be monitored | High | 1 | Yes
|  | g | Graphical / Geographical View | Google Map Integration / Automated Network graph plotting | High | 1 | Partial
|  | h | Docket management system ¦ Email | Acknowledgement of Alarms / Notifications/Resolution | Med | 2 | No
|  | i | Connected Devices | For AP only.. CGI unknown for other devices : TBD | Med | 2 | Partial
3 | Configuration : Device Level | [6 empty] | C
|  | a | Auto Discovery [Multiple Instances] | Ping / SNMP / Trace Route / SDM / UPNP | High | 1 | Partial
|  | b | Profile Templates | Common configuration settigns for all the devices of common type | High | 1 | Partial
|  | c | Config Task [To be defined in details, per case basis + Scheduling] | ? | Med | 3 | No
|  | d | Factory Reset | Single Click factory Resetfor group of devices. Manually and via Scheduling | High | 1 | Partial
|  | e | Firmware Upgrade [Manual / Scheduled] | Manual done ¦ Scheduled Remaining | High | 1 | Partial
|  | f | Firmware files Management | Storage of Firmware on Server | Med | 2 | No
|  | g | Individual Device Management [HTTP Frame] | Display the device confiuration page to the user | Med | 1 | Yes
|  | h | Route Management | Devices should opt the best possible path to interact with other devices. Support for Source NAT and Destination NAT | Low | 3 | No
|  | i | Schedule Management | Factory reset / Firmware Upgradation / Notification / Data backup / Performance log collection / Any other required Action | Med | 2 | No
|  | j | Inventory Management | Central point to remove / add / edit / disable / enable, the devices or a group of devices | Low | 2 | No
|  | l | Support for DCHP Relay Agent | Support for internal DHCP Server with scalability function and must be capable to redistribute dynamically learned information such as DNS, WNS and local DNS Suffix entries in the DHCP response. | Low | 3 | No
|  | m | Support for SSH/Telnet on the controllers. | Give the user interface to debug device problems by collecting the data | Low | 3 | No
4 | Reporting | [6 empty] | P
|  | a | Save Report on Server | Saving the filters | Med | 2 | No
|  | b | Historical Reports | Device Reports / Service Reports / User Reports / Network Reports / User Customized Reports | High | 2 | No
|  | c | Graph based Analytics | Alert Graphs / Device Graphs / Service Graphs / User Defined Graphs | High | 2 | Partial
5 | Accounting & Authentication | [6 empty] | S
|  | a | Usage, Time based billing | Hotspot Billing | Low | 3 | No
|  | b | ID based on IP/Mac/Username | through Radius | Low | 3 | No
|  | c | RADIUS Integration [with Proxy] | Through Radius | Low | 3 | No
|  | d | Support for multiple Authentication Types | Web Based / MAC Based / 802.1x / LEAP, PEAP, EAP-TLS, EAP-TTLS, EAP-SIM, EAP-AKA | Low | 3 | Partial
|  | e | Support for secure publish to LDAP and/or integrate via SQL, RADIUS, XML. |  | Low | 3 | No
6 | Interfaces
|  | a | Webbased Portal | On | High | 1 | Yes
|  | b | Northbound | SNMP / XMLSOAP / CORBA - For forwarding the NMS data to other 3rd party softwares | Med | 3 | No
|  | c | Notification System | SMS / EMAIL / XMPP Jabar | Med | 2 | Partial
7 | Scalability / Redundancy
|  | a | Handling Large Networks & Operation |  | Med | 3 | Partial
|  | b | Distributed System |  | Med | 3 | Partial
|  | c | Device Failover Management |  | Low | 3 | No
8 | Planning
|  | a | Wireless Coverage Planner [Indoor / Outdoor] |  | Low | 3 | No
|  | b | Network Design |  | Low | 3 | No
|  | c | Signal Strength |  | Low | 3 | No
9 | device list : integration
|  | a | APs | LBSNAA client requirement specification to be fullfilled | High | 1 | Partial
|  | b | Switches – 24 / 8 Port | Switch 24 Port / Switch 8 Port [SNMP based] Integration, for centralized configuration and monitoring | Med | 2 | No
|  | c | IP Radios | IDU 4 Port / IDU 8 Port Integration, for centralized configuration and monitoring | High | 2 | No
|  | d | E1 Radios | ODU 16 Mbps / ODU 100 Mbps device Integration, for centralized configuration and monitoring | High | 2 | No
|  | e | IP Cameras | Profile management like AP type devices | Med | 2 | No
|  | f | Home Gateway / Enterprise Gateway / Switch 4 Port |  | Low | 3 | No
10 | Third Party Tools : integration
|  | a | Support for comprehensive trouble ticketing system for subscriber interaction with support for tracking every request and service issue |  | Low | 4 | No
|  | b | Support for integrating with SIGTRAN/SS7 systems to effortlessly handle Mobile Data Offload to WLAN. |  | Low | 4 | No
|  | c | Support for Diameter Credit Control implementation for Credit control applications. |  | Low | 4 | No
|  | d | Support for one-time password (OTP) or PIN Generation for recharge & Account authentications and forwarding it to the SMS Gateway. |  | Low | 4 | No
|  | e | Support for integrating with major payment systems such as Credit & Debit cards, Internet banking systems, Paypal etc., |  | Low | 4 | No